## Sheet1
Name of Centre | CApIC
Institution | Covenant University, Ota |  |  | On Schedule
Country | Nigeria
Center Leader | Prof. Ezekiel F. Adebiyi |  |  | Behind Schedule
Annual Workplan (Month XXX-Month XXX, Year) | January - December, 2021
Work Plan Activities | Description | Partner Contribution (if relevant) | 2021 Y2Q1 |  |  | 2021 Y2Q2 |  |  | 2021 Y2Q3 |  |  | 2021 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: Centre Admin Readiness for Year 2
Sub-Action 1a: Attendance of trainings and ACE workshops
Activity 1: Arrange for Faculty and Staff to attend specialised trainings | To have both Faculty and Staff in the Centre to attend relevant trainings to enhance the quality of their delivery and effectiveness. These trainings can either be virtual or onsite. | To assist in hosting such trainings as appropriate. | [12 empty] | Increased number of faculty and staff trained in the centre operations | Not Applicable | 10000 | 0 | 0 | Centre Leader and Deputy Centre Leaders
Activity 2: Arrange for Faculty and Staff to attend ACE Impact workshops (virtual & onsite) | Plan to have the relevant Faculty and Staff attend all ACE Impact workshops (virtual and onsite). | Not Applicable | [12 empty] | Number of centre faculty and staff trained in ACE Impact Workshops. | Not Applicable | 30000 | 0 | 0 | Centre Leader and Deputy Centre Leaders
Sub-Action 1b: Procurement of essential office equipment and stationery
Activity 1: Provision of monthly running cost (imprest) | In order to ensure smooth running of the Centre Admin office, we plan to allocate money for imprest each month. | Not Applicable | [12 empty] | Effective centre adminstrative operational structure | Not Applicable | 2000 | 0 | 0 | Admin Officer, Project Accountant & Procurement Officer
Activity 2: Purchase and distribution of essential office equipment and stationery | To purchase all the required office equipment and stationery | Not Applicable | [12 empty] | A well furnished and equipped Secretariat. | Not Applicable | 3000 | 0 | 0 | Procurement Officer, Admin Officer & Project Accountant
Sub-Action 1c: Periodic meetings with partners and SAB
Activity 1: Arrange regular meetings with partners and SAB | To hold periodic meetings with all our partners (national and regional) and the members of SAB (online and onsite). | Not Applicable | [12 empty] | Recordings and minutes of meetings of the SAB and partners. | Not Applicable | 0 | 0 | 0 | Admin Head and Centre website Master
Action 2: DLI 3 Quantity of Students
Sub-Action 2a: DLI 3.1 (PhD students), DLI 3.2 (Masters students)
Activity 1: Recruit students for postgraduate programs, covering stipends, tuitions, etc | To recruit postgraduate students in the following programme:Biochemistry,Computer Science,Bioinformatics & Information and Communication Engineering(ICE) | To assist in attracting qualitfied students especially in the region. | [12 empty] | Increased number of postgraduate students enrolled for Masters and PhD programs of the centre. | Not Applicable | 148962 | 200000 | 0 | Centre Leader and Deputy Centre Leaders, Admin Officer & M&E Officer
Sub-Action 2b: DLI3.3 (Short Term Courses)
Activity 1: Organise training at CApIC-ACE and at national partners' sites | To organise training at the sites of our site and national partners | To assist in providing the needed logistics and advert for the trainings. | [12 empty] | Number of national partners trained by the Centre. | Not Applicable | 12000 | 50000 | 0 | Centre Leader, Deputy Centre Leaders, Communication Officer and Admin Head
Activity 2: Organise training of partners at regional partners' sites | To organise training at the sites of our regional partners' sites. | The regional partners to assist in providing the needed logistics for the trainings. | [12 empty] | Number of regional partners trained by the Centre | The training will enhance the effective delivery at the regional partners' sites for the Cancer genomics project. | 8000 | 10000 | 0 | Centre Leader, Deputy Centre Leaders, Communication Officer and Admin Head
Activity 3: Arrange conference attendance | To arrange for the Centre Faculty members, Staff and Students to attend both local and international conferences. The faculty and students also have joint publications accordingly. | Not Applicable | [12 empty] | Number of Faculty and Students sponsored by the Centre to attend both national and international conferences. | The presentations made by faculty and students at conferences are expected to lead to Journal publications. | 8000 | 0 | 0 | Centre's Administrator and the Communication Officer
Activity 4: Organise short professional courses | To organise short professional courses on cloud and HPC for students, professionals & researchers. | To provide the needed technical and logistics support for trainings. | [12 empty] | Increased number of National and Regional students and faculty trained in short-term courses. | Not Applicable | 11000 | 50000 | 0 | Centre Leader, Deputy Centre Leaders, Communication Officer and Admin Head
Action 3: DLI 4 (Quality of Education)
Sub-Action 3a: DLI 4.2a ACE International research publication with national partners & DLI 4.2b ACE International research publication with regional partners
Activity 1: Bio-banking of biospecimen at partner sites | To set up facilities for cancer specimen bio-banking at our partners' sites and conduct training | Our partners will be directly involved in the setting up process. | [12 empty] | Receipts and invoices, travels tickets, accommodation and pictures at the site of the partners | In order to fully commence research work, it is important for the bio-banking of our samples and data collection at the partners' sites. | 17000 | 5000 | 0 | Centre Leader and Deputy Centre Leaders, Procurement Officer, M&E Officer & PM
Activity 2: Sample processing for Cancer genomics research | To carry out DNA, RNA isolation, bisulfide conversion for our Cancer genomics project. | Not Applicable | [12 empty] | Documents on sample processing, laboratory notes, receipts and invoices on purchase of consumables. | Not Applicable | 10000 | 0 | 0 | Deputy Centre Director I, Core Centre Faculty (Cancer group), Applied Research Coordinator& M&E
Activity 3: Sequencing,PCR identification & validation | To carry out these activities under our Cancer genomics project. | Not Applicable | [12 empty] | Invoice and receipts on purchase of sequencer and its consumables, sequence results, lab notes and picture evidence of students' usage. | Not Applicable | 30000 | 100000 | 0 | Centre Director, Core Centre Faculty (Malaria group), Applied Research Coordinator & M&E Officer
Activity 4: Develop bioinformatics pipelines | Plan the development of bioinformatics pipelines for variant calling, differential expression analysis and ancestry informative markers. | Not Applicable | [12 empty] | Functional computational pipelines for our analysis | Not Applicable | 2000 | 0 | 0 | Centre Director, Applied Research Coordinator, Core Centre Faculty (Malaria&Cancer groups) & M&E Officer
Activity 5: Investigate Malaria resistant gene and genotype | To investigate Malaria-resistant gene and genotype association with aggressive PCa and BCa. | Not Applicable | [12 empty] | Malaria-resistant gene are identified. | Not Applicable | 1000 | 0 | 0 | Centre Director & Applied Research Coordinators
Activity 6: Investigate the treatment regimen and response in PCa & BCa | Carry these activities across our 3 research focus groups. | Not Applicable | [12 empty] | Development of treatment regime and response on available anticancer and antimalaria drugs. | Not Applicable | 1000 | 0 | 0 | Centre Director, Deputy Centre Directors & Applied Research Coordinators
Activity 7: Carry out simulation and modelling work | To carry out simulation and modelling of metabolic network in addition to data processing. | Not Applicable | [12 empty] | Simulation and Modelling works are carried out for Malaria treatment. | Not Applicable | 4000 | 0 | 0 | Centre Director, Deputy Centre Directors & Applied Research Coordinators
Activity 8: Conduct Structure based drug design (SBDD) | To conduct structure based drug design (SBDD) in silico only. | Not Applicable | [12 empty] | SBDD is carried out | Not Applicable | 3000 | 0 | 0 | Centre Leader and Deputy Centre Leaders
Activity 9: Develop virtual and/or high throughput screening (HTS) | To develop virtual screening with high throughput screeing and inhibitor design. | Not Applicable | [12 empty] | Virtual and High throughput screenings are conducted. | Not Applicable | 50000 | 0 | 0 | Centre Director, Deputy Centre Directors &Applied Research Coordinators
Activity 10: Purchase NMR instrument and conduct anti-plasmodial drug dev. and validation | Purchase NMR instrument and conduct anti-plasmodial drug dev. and validation including synthesis, structure validation & biological assay. | Not Applicable | [12 empty] | Anti-plasmodial drug validation is carried out. | Not Applicable | 575000 | 100000 | 0 | Centre Leader, Deputy Centre Leaders and Core Faculty members, Procurement Officer, Registrar, Director PPD, Safety Officer & M&E Officer
Activity 11: Conduct experimental validation of predicted targets | To conduct experimental validation of predicted targets e.g. inhibitor synthesis, structure validation, bioassay. | Not Applicable | [12 empty] | Expreimental validation will show the target genes. | Not Applicable | 39000 | 0 | 0 | Centre Director, Deputy Centre Directors & Core Centre Faculty members
Activity 12: Implement regulatory metabolic modelling | To conduct regulatory metabolic modelling-in silico only. | Not Applicable | [12 empty] | The regulatory metabolic modelling-in silico is done. | Not Applicable | 1000 | 0 | 0 | Centre Director, Deputy Centre Directors &Core Centre Faculty members
Sub-Action 3b: DLI 4.3a Infrastructure improvement for research and learning (procurement and civil works)
Activity 1: Renovate the Cancer Genomics laboratory | Renovate the approved temporary lab. | Not Applicable | [12 empty] | A furnished and equipped Cancer genomics laboratory | Not Applicable | 10000 | 10000 | 0 | Centre Leader, Deputy Centre Leader I, PM, PA, M&E and Procurement Officer
Activity 2: Build research infrastructure in the University | Establish insectary and insecticide testing research lab. | Not Applicable | [12 empty] | To construct a well-designed insectary | Not Applicable | 5000 | 0 | 0 | Centre Leader, Deputy Centre Leader I, PM, PA, M&E and Procurement Officer
Activity 3: Purchase of malaria research equipment | Purchase and install essential lab equipment for malaria research. | Not Applicable | [12 empty] | To procure and install laboratory equipment for malaria research | Not Applicable | 87000 | 50000 | 0 | Centre Leader, Deputy Centre Leader I, PM, M&E Officer, PA and Procurement Officer
Activity 4: Upgrade of FEDGEN cloud datacentre (2nd Phase) | 2nd phase of requirement elicitation, design, procurement and upgrade of the FEDGEN cloud datacenter | Not Applicable | [12 empty] | Functional FEDGEN cloud datacenter with 2nd phase of hardware and software installed. | Not Applicable | 81938.5 | 300000 | 0 | Deputy Centre Leader II, System Admin, PA,Communication Officer,PM & M&E Officer
Activity 4: Equip the FEDGEN computer laboratory | Procure laptops, multimedia equipment and set-up the FEDGEN computer laboratory for research activities by students and researchers at the Centre | Not Applicable | [12 empty] | Fully operational laptops and multimedia equipment in the FEDGEN computer laboratory. | Not Applicable | 6392 | 15000 | 0 | Centre Leader, Deputy Centre Leader II,, System Admin, PA, PM and Procurement Officer
Sub-Action 3c: DLI 4.2a ACE International research publication with national partners & DLI 4.2b ACE International research publication with regional partners
Activity 1: Recruit participants for sample and data collection under Malaria project | To engage those who will be involved in sample and data collection. | Not Applicable | [12 empty] | No of participants for sample collection | Not Applicable | 49941 | 0 | 0 | Centre Leader, Deputy Centre Leaders, M&E Officer & Applied Research Coordinators
Activity 2: Recruit participants for sample and data collection for Cancer genomics project | To engage those who will be involved in sample and data collection. | Not Applicable | [12 empty] | Filled questionaires from participants and collected data targeted towards good publications. | Not Applicable | 20000 | 0 | 0 | Centre Leader, Deputy Centre Leaders, M&E Officer & Applied Research Coordinators
Sub-Action 3d: DLI 4.1a (National Accreditation)
Activity 1: Revise and modify postgraduate curriculum in Biochemistry | To revise and modify postgraduate curriculum in Biochemistry for gap and self assesment, ready for international accreditation. | Not Applicable | [12 empty] | The reviewed curriculum with gap and self assessment completed | The review will enhance the quality of teaching and learning of the Biochemistry Postgraduate programme. | 200000 | 0 | 0 | Registrar, Centre Leader, HOD, DAPU and Deputy Centre Leaders
Activity 2: Review the CS and Bioinformatics curricula as part of preparation for international accreditation | To have these for Computer Sciences and the Bioinformatics programs. | Not Applicable | [12 empty] | The Centre in collaboration with the Computer and Information Sciences (CIS) Department at the University intend to carry out this process to enhance the quality of teaching and learning at the Department. | The review will enhance teaching, develop and strengthen research capacity of researchers & students. | 5000 | 0 | 0 | Registrar,Centre Leader,HOD,M&E Officer and Deputy Centre Leaders
Activity 3: Revise and modify ICE postgraduate curriculum as part of preparation for internatinal accreditation. | To revise & modify the Information and Communication Engineering (ICE) postgraduate curriculum to reflect loT & Big Data Analytics, Cloud & High Performance Computing and AI in Communication Systems.. | Not Applicable | [12 empty] | The Centre in collaboration with the Electrical and Information Engineering (EIE) Dept at the University intend to process this in order to improve the quality of the academic program. | The revision will enhance teaching, develop & strengthen research capacity of West/Central African students & researchers. | 1000 | 0 | 0 | Registrar,Centre Leader, HOD, M&E Officer and Deputy Centre Leaders
Activity 4: Prepare and submit quality manuscripts for research publications | To prepare and submit a reasonable amount of quality manuscripts from our 3 core research groups: Cancer genomics, Malaria & FEDGEN. | To collaborate in making the required input in having excellent research publications. | [12 empty] | Presentation of reputable journal publications | Not Applicable | 39126 | 0 | 0 | Centre Leader, Deputy Centre Leaders, M&E Officer and Academic Program Coordinator
Action 4: DLI 5 (Relevance of Education & Research)
Sub-Action 4a: DLI 5.1a External generated revenue from private sector
Activity 1: Provide research and related cloud and HPC services | To provide both onsite & offsite support for students & investigators. | To provide required ICT and logistic support. | [12 empty] | The students are provided with all they require to carry out outstanding research. | The contributions of the FEDGEN research group will greatly support the work of both the Malaria & Cancer genomics research groups. | 13200 | 50000 | 0 | Deputy Centre Leader II, System Admin, PA,Communication Officer,PM & M&E Officer
Activity 2: Provide research and related lab services for diagnosis (Malaria based) | To conduct genomic analyses for the detection & prediction of P. falciparum and other services. | Not Applicable | [12 empty] | The Centre intend to carry out these services as part of our IGR drive. | This will further contribute to our project under the malaria research. | 500 | 20000 | 0 | Centre Leader,Procurement Officer,PM,PA,M&E Officer
Activity 3: Provide support for students & investigators | Purchase the consumables needed to carry out the Activity 2. | Not Applicable | [12 empty] | Both Faculty members and Students at the Centre are provided with all they need to conduct effective scientific research. | The consumables will be needed for us to execute Activity 2. | 500 | 5000 | 0 | Centre Leader, Deputy Centre Leaders& M&E Officer
Activity 4: Provide research and related lab services (Cancer based) | To provide research & lab services such as diagnosis & precision oncology. | Not Applicable | [12 empty] | The Centre intend to carry out this services as part of the IGR drive. | The services will support the research work in the Cancer genomics group. | 5000 | 20000 | 0 | Deputy Centre Leader I, Research Coordinator, Procurement Officer & Project Accountant
Sub-Action 4b: DLI 5.2a Number of students with at least 1-month internship or staff with placement nationally & DLI 5.2b Number of students with at least 1-month internship or staff with placement regionally
Activity 1: Provide training for Centre personnel | To conduct training for the research assistants (RAs), Faculty members & staff at the Centre. | To help facilitate some of the sessions at the trainings. | [12 empty] | After the trainings, the RAs are expected to have better practical knowledge of their various programs. | The training will enhance the quality of the Centre's personnel. | 5000 | 0 | 0 | Deputy Centre Leader I, Research Coordinator, Communication Officer,PM & Admin Officer
Activity 2: Arrange internship for Faculty and students | To have internship for Faculty and students of the Centre. | To host some of the Faculty and students in the Centre for industry experience. | [12 empty] | To improve on the research capacity and expertise of the students. | The students are expected to have a first-hand experience of the industry during the period. | 500 | 120000 | 0 | Centre Leader, Deputy Centre Leaders, Core Centre Faculty (Internship Committee),PM,PA and M&E Officer
Sub-Action 4c: DLI 5.1b External generated revenue from other sectors
Activity 1: Write Proposal (FEDGEN project based, Malaria project based and Cancer Genomics project based) to attract research grants from Industries, donor agencies, Governments and Partners. | Submit proposals for funding on Cloud, HPC and Artificial Intelligence (AI),for upward validation and upscale for clinical trials and to attract research funding for Cancer genomics research | Will be involved as Co-Principal Investigators(Co-PI), Investigators and Industry Partners | [12 empty] | Number of research grants attracted to the Centre and the amount of grant funds in the IGR account. | The proposals will contribute to the sustainability plans of the Centre as well as training of more research students and Centre Faculty | 2000 | 1500000 | 0 | Centre Leader, Deputy Centre Leaders, Core Centre Faculty and Staff (FEDGEN group),PM & Project Accountant
Activity 2: Write Proposal (precision medicine based) to attract research grants from Industries, donor agencies, Governments and Partners | Submit proposal on precision medicine, combining the three research groups capacities in the Center | will be involved as co-I/PI | [12 empty] | Number of research grants attracted | The proposals will contribute to the sustainability plans of the Centre. | 500 | 1200000 | 0 | Centre Leader, Deputy Center Leaders, Centre Faculty and Staff, PM & Project Accountant
Action 5: DLI 7 (Institutional Impact)
Sub-Action 5a: DLI 7.1 University-wide regional strategy
Activity 1: Management and governance of ACE project | Improve the ICT facilities in the university. | Not Applicable | [12 empty] | Increased efficiency of Centre/University Management and Governance | Not Applicable | 200000 | 100000 | 0 | Centre Leader, Deputy Centre Leaders, Registrar, CSIS Director, Procurement Officer, F&M Officer, M&E Officer
[17 empty] | 1698559.5 | 3905000