## Procurement Plan Goods
Country: NIGERIA
Organisation: COVENANT UNIVERSITY, OTA
| Project/Programme: AFRICA CENTRE OF EXCELLENCE FOR COVENANT APPLIED INFORMATICS & COMMUNICATION (CApIC-ACE) | [7 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
Duration: JANUARY - JUNE, 2025
| GOODS |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  | Contract Implementation
S/N | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | [9 empty] | 1 wk |  | 1.5-3 wks
Actual
List of Contracts
1 | Procurement of Consumables for Cancer Research | CU/CApIC-ACE/ GOODS/25/01 |  | 13000 | National shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-01-23 | 13/02/202 | 20/02/2025 | N/A | Plan | 13000 | 27/02/2025 | 06/03/2025 | 2025-03-13 | 2025-03-20 | 2025-03-27 | 03/04/2025
[8 empty] | Actual | [7 empty] | Actual
2 | Procurement of Consumables for Malaria Research | CU/CApIC-ACE/ GOODS/25/02 |  | 22000 | National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-02-03 | 24/03/2025 | 31/03/2025 | N/A | Plan | 22000 | 08/04/2025 | 15/04/2025 | 2025-04-22 | 2025-04-29 | 2025-05-03 | 10/05/2025
[8 empty] | Actual | [7 empty] | Actual
3 | Maintenance of Cancer Genomics Laboratories | CU/CApIC-ACE/ GOODS/25/03 |  | 10000 | National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 20/01/2025 | 10/02/2025 | 17/02/2025 | N/A | Plan | 10000 | 24/02/2025 | 2025-03-03 | 10/03/2025 | 17/03/2025 | 24/03/2025 | 247/03/2025
[8 empty] | Actual | [7 empty] | Actual
4 | Purchase of Research Equipment for CRG Partner Sites | CU/CApIC-ACE/ GOODS/25/04 |  | 40000 | Direct Sourcing (DS) and National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-01-31 | 21/02/2025 | 28/02/2025 | N/A | Plan | 40000 | 07/03/2025 | 14/03/2025 | 21/03/2025 | 28/03/2025 | 04/04/2025 | 11/04/2025
[8 empty] | Actual | [7 empty] | Actual
5 | Procurement of Laptop for Bioinformatics Research Activities | CU/CApIC-ACE/ GOODS/25/05 |  | 3000 | National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-02-03 | 24/036/2025 | 29/02/2025 | N/A | Plan | 3000 | 07/03/205 | 14/03/2025 | 18/03/2025 | 21/03/2025 | 25/03/2025 | 29/03/2025
[8 empty] | Actual | [7 empty] | Actual
6 | Upgrade of In-Vitro Laboratory and Molecular Chemistry Laboratory | CU/CApIC-ACE/ GOODS/25/06 |  | 47000 | Direct Sourcing (DS) and National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2024-01-04 | 25/05/2024 | 20/06/2024 | N/A | Plan | 47000 | 25/06/2024 | 2024-05-07 | 2024-10-07 | 15/07/2024 | 15/08/2024 | 18/08/2024
[8 empty] | Actual | [7 empty] | Actual
7 | Procurement of Additional Equipment for the FEDGEN Data Centre | CU/CApIC-ACE/ GOODS/25/07 |  | 35000 | National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-02-10 | 03/03/2025 | 10/03/2025 | N/A | Plan | 35000 | 17/03/2025 | 247/03/2025 | 2025-03-31 | 2025-04-07 | 2025-04-14 | 21/04/2025
[8 empty] | Actual | [7 empty] | Actual
8 | Procurement of Essential Office Equipment and Accessories | CU/CApIC-ACE/ GOODS/25/08 |  | 3000 | National Shopping (NS) | N/A | Post | Plan | N/A | N/A | N/A | 2025-01-27 | 10/02/2025 | 24/02/2025 | N/A | Plan | 3000 | 03/03/2024 | 10/03/2025 | 2025-03-17 | 26/8/2024 | 2025-03-24 | 02/04/2025
[8 empty] | Actual | [7 empty] | Actual
| TOTAL AMOUNT |  |  | $173,000.00 | [12 empty] | $173,000.00
CBN EXCHANGE RATE: ₦1,534= U.S. $1.00