## Sheet1
Name of Centre: | Covenant Applied Informatics and Communication Africa Centre of Excellence (CApIC-ACE)
Institution: | Covenant University, Ota |  |  | On Schedule
Country: | Nigeria
Center Leader: | Prof. Emeka E. J. Iweala |  |  | Behind Schedule
Annual Workplan: | January 01 - June 30, 2025
Work Plan Activities | Description | Partner Contribution (if relevant) | 2025 Y5Q1 |  |  | 2025 Y5Q2 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun
Action 1: DLI 1 Centre Administration and Management
Sub-Action 1a (1.1 -1.5): Attendance of trainings and ACE workshops and Communication
Activity 1.1: Support for Faculty and Staff to participate in special trainings, workshops and conferences. | To have both Faculty and Staff in the Centre attend relevant trainings to enhance their effectivness and efficiency. These trainings can either be virtual or onsite. | Not applicable | [6 empty] | About twenty (20) faculty and staff trained in the centre and university operations. | The regular training of faculty and staff in the Center and University is a recurring activity to enhance effectiveness and understanding of the Center's activities. | 120000 | 0 | 0 | Centre Leader & Project Manager
Activity 1.2: Support for selected Faculty and Staff to attend ACE Impact Regional workshops and other meetings (virtual & onsite). | Plan to have the relevant Faculty and Staff attend ACE Impact Regional workshops (virtual and onsite). | Not applicable | [6 empty] | About five (5) centre faculty and staff participants in the ACE Impact Regional Workshop. | Attendance of the ACE Impact Regional Workshops is compulsory for all Centers in the project. | 50000 | 0 | 0 | Centre Leader, Deputy Centre Leader, M&E Officer, Project Manager, & Project Accountant
Activity 1.3: Organise trainings on sexual harrassment, environmental management and safeguard for Faculty, Staff and Students. | Plan to have all the Center's Faculty, Staff and Students to attend training sessions on sexual harrassment, environmental management and safeguard. This training will include Code of Conduct, grievance redress mechanism, General Laboratory Safety (standard operating procedures, control measures - administrative, engineering and procedural controls) procedures for proper labelling, storage etc; personal protective equipment, laboratory safety equipment, record keeping; medical consultation; and hands-on. | Not applicable | [6 empty] | Number of Center faculty, staff and students who received updated training on sexual harrassment policy and grievance reporting procedures. | The old and new personnel on the project must regularly be up to date as regards the approved policies and procedures of the Centre on sexual harrassment and grievance redress mechanisms. | 1000 | 0 | 0 | E&S Officer, Communication Officer & Project Manager
Activity 1.4: E&S Safeguard Implementation Support | Support for Environmental and Social Safeguard implemetation missions | Not applicable | [6 empty] | Preparation and submission of periodic safeguard reports on the implementation of E&S safeguards | The periodic safeguards reports from the Centre will be audited by the designated World Bank Consultant accordingly. | 4000 | 0 | 0 | Centre Leadership, E&S Officer & Project Manager
Activity 1.5: Upgrade of website and communication of centre activities and events. | The Center plans to continue upgrading its website, produce a documentary and issue periodic press releases as text stories or photostories in at least 2 reputable or most preferred national dailies. The stories will cover major activites, research and other relevant details of the Center. The link(s) of the press statement(s) will be made available on the Center's website and other social media handles after publication. | Our partners will provide supporting information on their partnership and involvement in centre-related activities. | [6 empty] | Increased communication of the Center's activities in the print, electronic and social media. | This activity is important to effectively communicate the Center's activities. | 13000 | 0 | 0 | Communication Officer, Industry Liaison Officer & Project Manager
Sub-Action 1b (1.6 - 1.7): Procurement of essential office equipment and stationery
Activity 1.6: Provision of monthly running cost (imprest). | In order to ensure smooth running of the Centre Admin office, we plan to allocate money for imprest each month. | Not Applicable | [6 empty] | Effective centre adminstrative operations. | Monthly imprest is required to effectively run the Center Administration. | 1000 | 0 | 0 | Admin Lead, Project Accountant & Project Manager
Activity 1.7: Purchase of essential office equipment and accessories. | To purchase required office equipment and accessories | Not Applicable | [6 empty] | Furnished and equipped Centre Offices. | Basic office items to be provided or replaced on a regular basis to aid the operations of the Center. | 3000 | 0 | 0 | Centre Leader, Admin Lead & Procurement Officer
Sub-Action 1c (1.8 - 1.10) Periodic meetings with partners, SAB and ISAB
Activity 1.8: Organisation of statutory meetings with partners (CRG, MRG & FEDGEN). | To hold periodic meetings (at least 2) with all our national and regional partners (online and onsite). | National and Regional partners are expected to attend the meetings. | [6 empty] | Recordings and minutes of meetings with our partners. | Regular meetings with our partners is a recurring event in the course of this project to ensure they are carried along with our plans and progress made. | 1000 | 0 | 0 | Center Leader, Deputy Centre Leader, M&E, Project Manager, Admin Lead, Applied Research Coordinator, Academic Officer, Project accountatnt, Procurement Officer, & Industry Liaison Officer
Activity 1.9: Organisation of statutory meetings with Sectoral Advisory Board (SAB). | To hold periodic meetings (at least 2) with our SAB members (online and onsite). | Not applicable | [6 empty] | Recordings and minutes of meetings with our SAB. | The meetings with our SAB is a recurring event in the course of this project to ensure they are carried along and fully engaged with our plans and progress made. | 1000 | 0 | 0 | Center Leader, Deputy Centre Leader, M&E, Project Manager, & Admin Lead
Activity 1.10: Organisation of statutory meetings with International Scientific Advisory Board (ISAB). | To hold periodic online meetings with our ISAB members. | Not applicable | [6 empty] | Recordings and minutes of meetings with our ISAB. | The annual meetings with our ISAB is a recurring event in the course of this project to ensure their support and contribution to what we do and progress made. | 1000 | 0 | 0 | Center Leader, Deputy Centre Leader, M&E, Project Manager, Admin Lead & Centre Website Master
Action 2: DLI 2 Development Impact
Sub-Action 2a (2.1 - 2.6) Development Impact Activities for External Evaluation
Activity 2.1: Organize two (2) Prostate and one (1) Breast Cancer awareness and screening outreaches. | Organize prostate cancer and breast cancer awareness outreaches and screening events within Ota and Lagos communities in partnership with Adodo-Ota Local government authorities and Non governmental Organisations. | Partners to provide venue and assist with publicity and logistics. | [6 empty] | About 1000 adult males and females from the Ota and Lagos communities will benefit from the programmes. | Awareness outreaches are platforms for impact to diseminate scientific and research information on breast and prostate cancer to the community in order to reduce the burden of the diseases. It also provides opportunity to colllect basic research data. The outreach programme will be advertised in the communities through relevant local authorities. Medical Information will be dissemminated to participants through physical seminars and distribution of medical information handbills and pamphlets. | 10000 | 0 | 2000 | Centre Leader, Project Manager, Applied Research Coordinator, Communication officer, Industry Liaison Officer & Cancer Research Group (CRG)
Activity 2.2: Support identification of actionable target for precision care of cancer at National level. | Carry out genetic screening for cancer patients in partnership with National Institute for Cancer Research and Treatment (NICRAT) identifying indigent cancer patients that will benefit from Nigerian cancer drug access program. | NICRAT will assist in recruitment of the patients. | [6 empty] | 50 cancer patients genetically screened | This will help identify indigent cancer patients that will benefit from Nigerian cancer drug access program | 5000 | 0 | 2000 | Centre Leader, Project Manager, Applied Research Coordinator, Communication officer & Cancer Research Group (CRG)
Activity 2.3: Malaria outreach, Stakeholder engagement and awareness program on World Malaria Day. | Organize malaria outreach within Ota with the Ogun State Ministry of Health, Ota primary health care workers and Local government on malaria eradication. | Ogun State Ministry of Health, and Ota primary health will assist in community engagement and awareness. | [6 empty] | About 500 participants will benefit, and record of pictures and stories of the event and awareness materials. | It is important to engage with the stakeholders to align our research with the governmental policies and strategies for malaria control | 5000 | 0 | 5000 | Centre Leader, Project Manager, Applied Research Coordinator, Communication officer & Malaria Research Group (MRG)
Activity 2.4: Surveillance studies on malaria incidence rates across partners' communities. | Conduct malaria surveillance to monitor malaria incidence within partners communities | Ogun State Ministry of Health, and Ota primary health will assist in community engagement and mobilisation for the programme. | [6 empty] | Malaria surveillance data from multiple partner communities will be obtained. | Epidemiological data for the region will be updated for improved malaria surveillance and control strategies. | 5000 | 10000 | 5000 | Centre Leader, Project Manager, Applied Research Coordinator & Malaria Research Group (MRG)
Activity 2.5: Showcase the FEDGEN-PHIS to the public during all Cancer Awareness Outreaches by the CRG and Malaria Outreaches by the MRG. | Collaborate with CRG and MRG to create awareness on the public health education content on FEDGEN-PHIS during Cancer and Malaria outreaches respectively. | Similar public awareness would be initiated at Afe Babalola University (ABUAD), LandMark University (LMU) and L'Université Libre des Pays des Grands Lacs (ULPGL), Democratic Republic of Congo. | [6 empty] | Increased number of registered public users as well as engagements (views, likes etc)on FEDGEN-PHIS. | The CApIC-ACE objective of enhanced public health education on malaria and cancer will be achieved and sustained. | 1000 | 0 | 500 | Center Leadership and FEDGEN Research Group (FRG)
Activity 2.6: Organise Traning on FEDGEN-DataHub and FEDGEN-CodingHub physically at LMU, ABUAD, CRG and MRG partner sites as well as virtually at ULPGL Democratic Repulbic of Congo and other foreign partner sites. | Collaborate with our pathners to enhance computational skills among researchers and students using our private cloud platforms. | Provision of venue and facilitators | [6 empty] | Increased number of active users for the FEDGEN-DataHub and FEDGEN-CodingHub. | The CApIC-ACE objective of improved HPC skills in Africa and storage of sensistive health data on indigenous platforms for privacy preservation. | 5000 | 0 | 0 | Center Leadership and FEDGEN Research Group (FRG)
Action 3: DLI 3 Quantity of Students
Sub-Action 3a (3.1): DLI 3.1 (PhD students), DLI 3.2 (Masters students)
Activity 3.1: Provide adequate support for all the current students of the Centre at Covenant University. | To provide for the payment of students' school fees, stipends, accommodation and other essentials for their successful stay on campus and completion of their programmes. | Not applicable | [6 empty] | A total of 115 regional and national postgraduate students of the Centre (43 Ph.D and 60 Master's) will be supported according to their scholarship categories in the 2024/2025 academic session. | This will ensure that our current students are adequately supported to complete their academic programmes seamlessly | 326379 | 0 | 0 | Deputy Centre Leader, Dean School of Postgraduate Studies, M&E Officer, Project Accountant, Admin Lead & Project Manager
Sub-Action 3b (3.2 - 3.8) DLI 3.3 (Short Term Courses)
Activity 3.2: Organise Cancer Genomics Workshop for facuty, staff and students. | Partnership with ISN to Organize hands-on workshop on cancer genomics. | ISN will provide reagents and technical support for the workshop | [6 empty] | 100 faculty, staff and postgraduate students trained | This training will strengthen the research capacity of faculty and students in gene sequencing | 1000 | 0 | 30000 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 3.3: Organise Cancer Genomics and Precision Oncology Conference | Partnership with Prostate Cancer Transatlantic Consortium (CaPTC), Prof Odedina, ACEMedicare Clinic, University of Nigeria Teaching Hospital (UNTH), Lagos State University Teaching Hospital (LASUTH), to organize a conference on Cancer genomics for African population | CaPTC, Prof Odedina, ACEMedicare, UNTH, LASUTH will provide resource persons | [6 empty] | 100 participants at the conference | This conference will provide the platform to share the research information and results on Cancer genomics | 5000 | 0 | 3000 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 3.4: Organise professional training on Cancer Genomics for postgraduate Students, Faculty and Clinicians | This is a paid short term professional workshop on Cancer genomics targeting mostly faculty, postgraduate students and Clinicians | Our Partners will provide resource persons and reagents | [6 empty] | 100 faculty, postgraduate studnets and clinicians trained | This training will strengthen the research capacity of faculty, students and clinicians in cancer genomics research | 10000 | 35000 | 3000 | Centre Leader, Project Manager, Applied Research Coordinator, Communication officer & Cancer Research Group (CRG)
Activity 3.5: Organize Malaria Genomics and Microscopy and Insect management Workshop at Covenant University | Organize hands on training workshop on malaria genomics analysis such as quality control, variant calling and annotation | Students and researchers from partner sites will participate in the training | [6 empty] | Picture evidence, attendance and certificates | This training will improve genomics research capacity of faculty and students | 15000 | 0 | 5000 | Centre Leader, Project Manager, Applied Research Coordinator & Malaria Research Group (MRG)
Activity 3.6: Organise the 4th HPC Workshop(hybrid) as a short-term professional training on Cloud & High Performance Computing(C&HPC) for postgraduate students and practitioners. | This training is to provide an indepth knowledge of cloud and high performance. It will be hybrid (online and onsite) with facilitators drawn from global IT giants. The target participants are research students, researchers and practitioners. | Academic and industry partners to assist with providing facilitators, logistic and funding support. | [6 empty] | To enhance the knowledge base of postgraduate students, industry practitioners and researchers on Cloud and HPC. | This will provide state-of-the-art skills and hands-on experience on Cloud and HPC for postgraduate students, industry practitioners and researchers. | 15000 | 0 | 20000 | Deputy Center leader, FRG Team Members, M&E Officer, Communication Officer, Project Accountant & Procurement Officer.
Activity 3.7: Provide funding for professional training/certification on cloud computing and other IT related certifications | FEDGEN postgraduate students, faculty and staff. will be required to get trained and obtain professional certifications on public cloud computing solutions(i.e. Azure, Google Cloud) | Industry Stakeholders (i.e. Microsoft, Google Cloud) to provide online trainings and certifications to improve technical capacity on cloud computing for FEDGEN postgraduate students, faculty and staff. | [6 empty] | To improve the capacity of a total of 8 students, faculty, staff and researchers on cloud computing | The cloud computing professional certification will improve the value delivery of the participants. | 10000 | 0 | 10000 | Deputy Center Leader, FEDGEN Research Group (FRG), Microsoft, Google Cloud
Activity 3.8: Support students for attendance of conferences. | Conference for faculty and staff on AI, Cloud Computtting, Cyber security, Telecommunication and Information System | Co-Authurship of publications with the CRG, MRG and our pathners in LMU, ABUAD, ULPGL DRC | [6 empty] | Number of persons that attended conferences and presented papers. | Increase Visibility of our research activities and products as well as collaboration with experts in the field | 5000 | 0 | 0 | Deputy Center Leader, FEDGEN Faculty and Staff, Project Manager
Action 4: DLI 4 (Quality of Education)
Sub-Action 4a (4.1- 4.5): DLI 4.2a ACE International research publication with national partners & DLI 4.2b ACE International research publication with regional partners
Activity 4.1: Biospecimen collection, processing, storage, DNA/RNA (cDNA synthesis), library preparation and Sequencing | Collect and process biospecimen for genomics sequencing in partnership with partner sites | Partners to assist in collection and processing of biospecimen | [6 empty] | Processed and sequenced biospecimen | This is to meet our research objectives and joint research publications | 10000 | 0 | 5000 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 4.2: Bio-banking of biospecimen from Cancer patients | The biospecimen will be collected from our partner sites | To assist with patient recruitment, data collection and processing | [6 empty] | Biospecimen to be recorded | This is to meet our research objectives and joint research publications | 5000 | 0 | 2000 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 4.3: Malaria epidemiological study and resistance mapping Malaria Survellance and Biobanking (of blood samples, filter paper blots) | Participants recruitment, Sample/data collection, processing for genomics | To assist with patient recruitment, data collection and processing | [6 empty] | Surveillance data, results and lab notes | This is to meet our research objectives and joint research publications | 10000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator & Malaria Research Group (MRG)
Activity 4.4: Malaria DNA/RNA (cDNA synthesis), Gene amplification and Protein, and Sequencing | DNA/RNA extraction for sequencing and mutational burden analysis | Not applicable | [6 empty] | Lab notes, PCR amplicons and sequenced data | This is to meet our research objectives and joint research publications | 5000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator & Malaria Research Group (MRG)
Activity 4.5: Preparation and submission of journal manuscripts co-authored with National and Regional Partners by FEDGEN Research Group (FRG) | To prepare and submit as many manuscripts on FEDGEN projects as are derived from our research and development activities. | Our national and regional partners will be co-authors of manuscript bssed on collaboratuve works. | [6 empty] | Number of published journal articles in Scopus indexed outlets | To meet CApIC-ACE objective of quality publications in collaboration with national, regional and international partners | 6000 | 0 | 10000 | Deputy Center leader, FEDGEN Team Members and Project Manager
Sub-Action 4b (4.6 - 4.14) DLI 4.3a Infrastructure improvement for research and learning
Activity 4.6: Purchase of consumables (for cancer research) | Procurement of reagents for analysis of biospecimen | Not applicable | [6 empty] | Increase in cancer genomics data of Africans | This is to meet our research objectives | 13000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator, Procurement Officer & Cancer Research Group (CRG)
Activity 4.7: Purchase of consumables (for malaria research) | Procurement of reagents for analysis of biospecimen | Not applicable | [6 empty] | Increase in malaria epidemiology/genomics data from the region | This is to meet our research objectives | 22000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator, Procurement Officer & Malaria Research Group (MRG)
Activity 4.8: Maintenance of cancer laboratory. | Purchase, replacement and repair of basic laboratory infrastructure and equipment | Not applicable | [6 empty] | Optimal functional lab and equipment | This is for continous research activities | 10000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator Procurement Officer & Cancer Research Group (CRG)
Activity 4.9: Purchase of equipment (CRG partner sites) | We plan to purchase basic equipment such as Centrifuges, freezers etc. and install at partners sites | Selected partners to provide the space and manpower for the installation of the equipment | [6 empty] | Equipped partner sites for short term biospecimen storage | This is for collaborative research with partners | 40000 | 0 | 10000 | Centre Leader, Project Manager, Applied Research Coordinator, Procurement Officer & Cancer Research Group (CRG)
Activity 4.10: Purchase of 1 Laptop for Bioinformatics Research activities | The laptops (HP EliteBook 840 G9 12th Gen Intel® Core™ i7-1255U up to 4.7 GHz Processor 16GB DDR4-3200 MHz RAM ¦ 512GB . ($1,300.00 each)) will be used as resource materials for the facilitators of the bioinformatics workshop and it will be used for the continous training of students. | Not applicable | [6 empty] | The laptop will improve the facilitation of bioinformatics trainigs | To support teaching efficiency | 3000 | 0 | 0 | Center Leader, Deputy Center Leader, Director, Centre for Systems and Information Services, Malaria Research Group (MRG), Procurement Committee, Project Accountant, Project Manager & M&E Officer
Activity 4.11. Upgrade of in vitro laboratory and molecular chemistry laboratory. | Purchase of chemical consumables, for the synthetic chemistry laboratory where the synthetic drug-like candidates will be synthesized | Not applicable | [6 empty] | Optimal functional laboratory | The equipment are needed to facilitate better research output. | 47000 | 0 | 0 | Center Leader, Deputy Center Leader, Malaria Research Gropu (MRG), Procurement Officer, Project Accountant, Project Manager & M&E Officer
Activity 4.12: Continous procurement, upgrade and maintenance of Cloud, HPC, RF and Edge-AI infrastructures for FEDGEN Datacenter and Testbeds. | We plan to procure additional equipment for the FEDGEN Datacenter and testbeds. These include HPC servers, Edge-AI, RF/networking equipment and components. This is to upscale the infrastructure for cloud computing and related technologies for the research communities and relevant industrial stakeholders. Continuous maintenance of the infrastructure for uniterruptred operation is also planned. | FEDGEN Cloud Consultant, Facility Manager, HPC Engineering Interns and collaborating institutions that are hosting FEDGEN Testbeds to work with the group for desired continuous procurement, upgrade and maintenance. | [6 empty] | Continuous upscaling of high performance computational resources for research computing in the cloud and on the edge. | This is for collaborative research with partners | 35000 | 0 | 10000 | Center Leader, Deputy Center Leader, Director, Centre for Systems and Information Services, Procurement Committee, Project Accountant, Project Manager & M&E Officer
Activity 4.13: Deployment of Region 5 FEDGEN Testbed to ULPGL Democractic Repulic of Congo and training of collaborators, faculty and staff at ULPGL. | Region 5 of the FEDGEN Testbed to be deployed to ULPGL, DRC and federated with the other 4 region at Covenant University, Landmark University and Afebabalola University | They would provide the location for deployment and maintenenace support for the equipment | [6 empty] | Functional Testbed at ULPGL, DRC site that could be monitored on the FEDGEN monitoring platform (https://monitor.fedgen.net) | Improved high perofmamce computational infrastructure for research within the Africa region | 25000 | 0 | 5000 | Center Leader, Deputy Center Leader, Director, Centre for Systems and Information Services, Procurement Committee, Project Accountant, Project Manager
Activity 4.14: Iterative/Continuous design, implementation, deployment and maintenance of FEDGEN_HealthEduApp Cloud Applications (i.e. FEDGEN-PHIS and FEDGEN-DataHub) and FEDGEN CodingHub. | Periodic Bootcamps will be organised for partners participation as well as outreaches/trainings in our partner sites. FEDGEN-PHIS(https://fedgen.net/phis) is an online knowledge base for public health information on Malaria and Cancer. It is currently hosted on the FEDGEN private cloud platform with the URL (https://fedgen.net/phis) and contain language translation and speech-to-text features. We intend to engage Software Development Interns (SDI) periodically to work with team for continuous design upgrade, impelementation and testing of the cloud application. FEDGEN-DataHub is an online repository where "omics" datasets collected by the Malaria and Cancer Group from research subjects within Africa are archived. We intend to carry our continous design upgrade, implementation and maintenance of the application. We will also organise periodic Bootcamps and outreaches/trainings in collaboration with our DSTN and academic partners on the two applications. FEDGEN-Coding(https://codinghub.fedgen.net) is our home grown customization of Juputer Notebook for cloud based coding with Python, R, C/C++ etc similar to Google Colab. This is accessible online to all FEDGEN research partners and students from anywhere in the world for AI, bioinformatics, chemoinformatics and engineering simulation workloads. | The different phases of the apps development lifecycle, Bootcamps,outreaches/trainning will be carried out in collaboration with CEA-MITIC, Senegal - our DSTN partner as well as our academic partners(Landmark University, ABUAD and ULPGL@ Goma, DRC). | [6 empty] | Functional FEDGEN PHIS, DataHub and CodingHub on the FEDGEN Datacenter, our private cloud platformn | Enhancement of public health education through expert reviewed articles on PHIS, secured storage of sensitive health data within our private cloud facility and improved access to computational and storage resources by researchers and postgraudate students within the African region | 5000 | 0 | 0 | Center Leader, Deputy Center Leader, FEDGEN Software Engineering Subgroup Team Lead, Collaborators on FEDGEN-HealthEduApp in MRG and CRG, Procurement Officer, Project Accountant, Project Manager
Action 5: DLI 5 (Relevance of Education & Research)
Sub-Action 5a (5.1 -5.5): DLI 5.1a External generated revenue from private sector
Activity 5.1: Grant development and writing retreat for MRG, CRG & FRG (Cloud & High Performance Computing with DSTN Partners) | We plan to have at least two grant development and writing retreat in the year for the members of CApIC-ACE | Selected national and regional partners will be involved by providing relevant details and documents needed for the various applications | [6 empty] | Five (5) research grant proposals worth at least 100,000 USD each submitted for funding considerations. 300,000 USD is projected to be realised from successful applications by July while the balance of 200,000 USD is projected to be realised from successful applications by November. | This will generate income for sustainabilty of the centre and harmonisation of research goals | 10000 | 200000 | 0 | MRG Team Members, CRG Team Members, FRG Team Members, M&E Officer, Project Accountant, Project Manager & Admin Lead
Activity 5.2: Commence ISO Certification of centre Labs | We plan to coomence the process of ISO certifiation for our labs in preparation for the provision of commercialised services. | AstraZeneca, Illumina/ISN and ISO consultant | [6 empty] | At least three (3) labs to be ISO certified | ISO certification of our labs will generate income from provision of lab services. | 30000 | 0 | 0 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 5.3: Provide paid research and related laboratory services for cancer genomics | Engage in research contract for genomic analysis | Not applicable | [6 empty] | Record of paid laboratory services provided | This will generate income for sustainabilty of the centre and provide services to the community | 4000 | 20000 | 0 | Centre Leader, Project Manager, Applied Research Coordinator & Cancer Research Group (CRG)
Activity 5.4: Organise Bootcamp for business strategy development for the upgraded FEDGEN Datacenter, Create aggresive marketing awareness to attract subscriptions for the available services on the Datacenter, Renew the engagement of FEDGEN Cloud Consultant for one more year to strengthen the technical robustness of the Datacenter. | The Bootcamp will involve facilitation by FRG/MRG/CRG Team members and partners as well as CApIC-ACE Cloud, Business and IP Consultants towards developing improved and realistic business strategy for: i) creating marketing campaigns ii) sustainable income generation strategies from the upgraded FEDGEN Datacenter. | Our academic and industry partners will faciliate at the bootcamp and provide linkages for potential subscribers. | [6 empty] | Functional FEDGEN Datacenter, Online subscription plans for clients, Income to the center's IGR account | Research computing services will be provided for researchers and research students at subsidised rate compared to commercial cloud platforms. | 3000 | 20000 | 0 | Deputy Centre Leader, FRG/MRG/CGR Members, Project Manager, Applied Research Coordinator, FEDGEN Cloud Consultant, Business Consultant, IP Consultant
Activity 5.5: Organize launching of endowment fund for the centre | We plan to collaborate with our host university to oraganise a lauching of an endowment fund for the centre | Our host University will provide logistics related to identifying and reaching out to potential Launchers of the endowment fund. | [6 empty] | Amount of money raised from the launch of endowment fund | This will generate income for sustainabilty of the centre and harmonisation of research goals | 10000 | 20000 | 0 | Centre Leader, Deputy Centre Leader, M&E Officer, Admin Lead &Project Manager, & Covenant University Management
Sub-Action 5b (5.6): DLI5.3 Number of new entrepreneurship, innovations, start-up companies, and commercialization support programs
Activity 5.6: Provision of services through the use of NMR and Sequencer | Provide paid laboratory services using the NMR and sequencer | Not Applicable | [6 empty] | Record of paid laboratory services provided | This will generate income for sustainabilty of the centre and provide services to the community | 10000 | 30000 | 0 | Centre Leader, Project Manager, Lab Technologist, Applied Research Coordinator & Malaria Research Group (MRG)
Action 6: DLI 6 Fiduciary Enhancement
Sub-Action 6a (6.1): DLI 6.1 Timely fiduciary reporting
Activity 6.1: Financial Report and EEP | Provide timely financial report and EEP | Not Applicable | [6 empty] | Completed financial report and EEP documents | This is required for proper financial records | 700 | 0 | 0 | Centre Leadership, Project Accountant & M&E
Sub-Action 6b (6.2): DLI 6.2 Functioning internal audit unit
Activity 6.2: Internal and External Audit Reports | Provide Internal and External Audit Reports | Not Applicable | [6 empty] | Completed Internal and External Audit Reports | This is required for proper audit records | 700 | 0 | 0 | Centre Leadership, Project Accountant & Internal Auditor
Sub-Action 6c (6.3): DLI 6.3 Web transparency on fiduciary reports
Activity 6.3: Upload of Financial reports and documents | Timely upload of Financial reports and documents on Centre website | Not Applicable | [6 empty] | Complete Upload of Financial reports and documents | This is required for financial transperancy | 500 | 0 | 0 | Centre Leadership, Project Accountant & Webmaster
Sub-Action 6d (6.4): DLI 6.4 Quality of procurement planning
Activity 6.4: Procurement Audit | Provide procurement audit | Not Applicable | [6 empty] | Completed Procurement Audit | This is required for procurement transperancy | 500 | 0 | 0 | Centre Leadership, Project Accountant, Internal Auditor & Procurement Officer
Action 7: DLI7 Institutional Impact
Sub-Action 7a (7.1 ): DLI 7.3a ACE host university adopts GAP analysis as part of international accreditation
Activity 7.1: To support faculty and staff from the Academic Planning Unit and the Quality Assurance and Academic Standards Committee to undergo training on national and international standards and best practices in higher education. | To provide training for faculty and staff from the Academic Planning Unit and the Quality Assurance and Academic Standards Committee on national and international standards and best practices in higher education. | Not Applicable | [6 empty] | 7 members of the faculty and staff trained on national and international best practices in higher education activities | The training is expeted to boost the efficient and effective service delivery of the participants. | 20000 | 0 | 0 | VC, Registrar, Director CSIS, Quality Assurance and Academic Standard Committee Chair, DLI 7 Focal Point, Center Leader, Deputy Center Leader, Project Manager, M&E Officer & Head Admin
Sub-Action 7b (7.2): DLI 7.4 ACE host university participate in PASET
Activity 7.2: Upgrade of University portal and digitisation of our processess | (1)Automation of the university attendance system, (2)Continous upgrade of the automation of level advising system, (3) Design and implementation of an online inventory system with scanners for research centers. | Not applicable | [6 empty] | Purchased of biometric attendance machines, Deployed and running attendance management system, Active level advising system within the university portal. | Efficient capturing of student attendance data and improved level advising. | 65000 | 0 | 10000 | VC, Registrar, Director of Academic Planning, DLI 7 Focal Point, Director of CSIS, and Chair of Quality Assurance & Academic Standards Committee
Sub-Action 7c (7.3): DLI 7.6 ICT Services for Innovation in Teaching and Research
Activity 7.3: Establishment of a state of the art pueson vue center, payment and renewal of subscriptions, as well as maintenance of ICT facilty already deployed for use within the University | (1)The pueson vue center is to provide international testing center for the university and the entire community to take tests related to variety of different professions. (2) Renewal of most of the existing software subscriptions and pay for new ones, as well as manage the ICT facilities deployed for use through the NgREN platform. | Not applicable | [6 empty] | Established location for Puesonvue center, well furnished pueson vue center with, purchased of all require IT equipment required for the setting up of the center | Serve as a revenue stream for the center and also provide ease of access to certification to the university. | 55000 | 10000 | 0 | VC, Registrar, Director CSIS, Center Leader, Deputy Center Leader, Infrastructure Engineer, Project Manager, M&E Officer & Head Admin
[11 empty] | 1058779 | 345000 | 137500